## Sheet1
Somerton project plan. This sets out the topics we will need to consider and indicative timescales. Please note, the timings may change
| 2021 | 2022 |  |  |  | 2023 | 2024 | 2025 | 2026
NCH Key Milestones | Oct - Dec | Jan – March | April – June | July – Sept | Oct –Dec
Community Engagement
Steering group meetings
Community events
Design Development
Surveys
Consider the areas
Look at housing need
Look at energy and sustainabilty
Look at potential land purchases
Carry out design work
Cost analysis
Approvals
Welsh government approvals
Sustainable drainage process
Pre application planning process
Planning approval consultation process (PAC)
Planning approval process
NCH contract approvals
Residents
Talk to residents about re -housing need and circumstances
Voluntary homeowner purchase available
Work up offer for home owners
Refurbishment
Consider works for refurbishment homes
Consider pilot refurbishment scheme
Carry out refurbishment works
Procurement
Select the contractor for refurbishment works
Select the contractor for regeneration works
On Site / Construction
Re-house residents (by phase)
Phase 1 regeneration works
Phase 2 regeneration works (start)
Future phases maybe required